## table
Component 1 - Overall Plan of Activities - November 2017 - November 2018
ID | DESCRIPTION | RESULT | [10 empty] | COUNTRY | INVOLVED ENTITIES | C/H | Y2 |  | Y3 |  | Y4 | [13 empty] | Y 4 |  | ID
[20 empty] | S1 | [5 empty] | S2 | [7 empty] | S 1
[16 empty] | M 24 | M25 | M36 | M37 | M38 | M39 | M40 | M41 | M42 | M43 | M44 | M45 | M46 | M47 | M48 | M35 | M36 | M37 | M38 | M39
|  | R1 | R2 | R3 | R4 | R5 | R6 | R7 | R8 | R9 | R10 | R11 |  |  |  | XI 16 | XII 16 | XI 17 | XII 17 | I 18 | II.18 | III.18 | IV.18 | V.18 | VI.18 | VII.18 | VIII.18 | IX.18 | X.18 | XI.18 | X.17 | XI.17 | XII.17 | I.18 | II 18
0.1 | Selection of sub-topics to be covered under specific year | [34 empty] | 0.1 | bar: M 24 to M37; S2 M35 to S2 M37
0.2 | TOR, selection, recruitment CN & European expert | [34 empty] | 0.2 | bar: M 24 to M25; M37 to S1 M39; S 1 M38 to S 1 M39
0.3 | TOR Situation analysis & Best practices under specific sub-topics | [34 empty] | 0.3 | bar: M 24 to M25; M37 to S1 M39; S 1 M38 to S 1 M39
1 | Identification Phase | [34 empty] | 1
1.1. | Situational Analysis | [34 empty] | 1.1.
1.1.1 | In-depth analysis on topic 1.1.3 (Vocational training)
1.1.2 | In-depth analysis on the topics 1.1.3,1.2.3,1.3.5 (Social security and other redistribution regulations and policy tools ) |  |  |  | R4 | [7 empty] | CHINA | EU MS (RE)/MCS | C | [20 empty] | 1.1.1 | bar: M25 to S2 M45
1.1.3 | In-depth analysis for topics 1.3.3, 1.4.3 (universal income) | bar: M37 to S2 M44
1.1.4 | In-depth analysis for topic 1.3.8 (informal sector integration) | bar: M37 to S2 M45
1.1.5 | In-depth analysis on the topic 1.2.4 (gender considerations) | bar: S1 M41 to S2 M37
1.2 | Identification and review of possible relevant EU experience | [34 empty] | 1.2
1.2.1 | Preparation of Country Reports on the topics 1.1.3, 1.3.5, 1.3.8 |  | R2 | R3 | R4 | R5 | [6 empty] | EU | EU MS | C | [20 empty] | 1.2.1 | bar: M25 to M37
1.2.2 | Preparation of Country Reports on the topic 1.2.4 |  |  |  | R4 | [7 empty] | EU | EU MS (CC) / Main Chinese stakeholders | C | [20 empty] | 1.2.3 | bar: S2 M36 to S 1 M39
1.3 | Panel discussions with stakeholders on the Identification Phase | [34 empty] | 1.3
1.3.1 | Panel discussion on topics 1.1.3, 1.3.5, 1.3.8 |  |  |  | R4 | [7 empty] | EU/ CHINA | EU MS/ Main Chinese stakeholders | C | [20 empty] | 1.3.1.1 | bar: S2 M44; S2 M35 to S2 M36
1.3.2 | Panel discussion / International workshop on topic 1.2.4 |  | R2 | R3 | R4 | R5 | [6 empty] | EU | EU MS/ Main Chinese stakeholders | C | [20 empty] | 1.3.2 | bar: S 1 M39
Analisys Phase | Analysis Phase | [34 empty] | Analysis Phase
1.4 | Specific analysis of relevant EU experience | [34 empty] | 1.4
1.4.1 | European research report on the topic 1.2.4 (gender considerations) | bar: S1 M39 to S2 M46; S2 M35 to S2 M37
1.4.2 | Technical feasibility of EU MS Best Practices to be introduced in China and preliminary reform proposals about the specific topics |  |  |  | R4 | [7 empty] | CHINA | EU MS(RE)/MCS | C | [20 empty] | 1.4.1.1 | bar: M25 to S2 M46; S 1 M38 to S 1 M39
1.4.3 | Definition of a first draft of reform proposal |  | R2 | R3 | R4 | R5 | [6 empty] | CHINA | EU MS/MCS | C | [20 empty] | 1.4.2 | bar: S2 M46 to S2 M47; S 1 M39
1.5 | Training/Study Assignments to EU countries | [34 empty] | 1.5
1.5.0 | 2-weeks traing on Evaluation of Social protection policies (topic 1.2.2) (carried over from 2017) | [34 empty] | 1.5.1 | bar: S1 M38
1.5.1 | 2-Weeks training on Monitoring interaction between Employment and Social security policies (topic 1.1.3) (carried over from 2017) | bar: S2 M47
1.5.2 | NDRC vice-chairman visit to EC, Spain | bar: S1 M41
1.5.2 | 8 days study visit on issues related to informal sector integration in social security schemes (topic 1.3.8) | [34 empty] | 1.5.2 | bar: S1 M41; S2 M35
1.6 | Worshop with stakeholders on the Analysis Phase | [34 empty] | 1.6
1.6.1 | Seminar on Active LabourMarket Policies | bar: M36
1.6.2 | Seminar on Gender considerations in pension reform | bar: S2 M47
1.6.3 | International workshop on issues related to informal sector integration into social security schemes (topic 1.3.8) |  |  |  | R4 | [7 empty] | EU/ CHINA | EU MS/ Main Chinese stakeholders | C | [20 empty] | 1.6.1 | bar: S1 M41; S2 M35
1.7 | Elaboration of reform proposals | [34 empty] | 1.7
1.7.1 | Final identification of reform proposals on topics 1.1.3,1.3.5,1.3.8 |  |  |  | R4 | [7 empty] | EU/ CHINA | EU MS | C | [20 empty] | 1.7.2.1 | bar: S2 M46
1.7.2 | Final identification of reform proposals on topic 1.2.4 | bar: S2 M47
Follow Up Phase | [35 empty] | Follow Up Phase
1.8 | Pilot activities | [34 empty] | 1.9
1.8.1 | Cooperation on Statistics management, Guangdong | bar: S1 M43 to S2 M44
1.8.2 | Cooperation on awareness raising on the importance of SS, Qingyuan | bar: S1 M43 to S2 M44
1.8.3 | Research report on long term care, Shanghai | bar: S2 M44
1.8.4 | SH overseas Provincial study visit on ageing | [34 empty] | 1.9.1 | bar: S2 M47
Horizontal macro activities | [35 empty] | Horizontal macro activities
1.9 | Coordination meeting in Italy | [34 empty] | 1.10 | bar: M37; S2 M36
1.1 | Reporting and Evaluation | [34 empty] | 1.11
1.10.1 | Component reports | [34 empty] | 1.11.2 | bar: M 24; M36; S1 M42; S2 M48; S2 M36
1.11 | PAC meetings |  |  |  | R4 | [7 empty] | EU/ CHINA | EU MS | C | [20 empty] | 1.12 | bar: S1 M39; S2 M36
Topics: 1.1.1-Social insurance administration systems reform (Preparation of the XIIIth Five-years Plan); 1.1.2-Coordination of policy making among government agencies in areas related to social protection reform; 1.1.3 Monitoring interaction between employment promotion and social protection policies； 1.2.1-Relationship of pension benefit with minimum social wage; 1.2.2-National policy evaluation technique in the area of social protection (indicators, methods and programs); 1.2.3 - Affordability of Pension schemes (contributions and Government subsidies); 1.2.4 (new) Gender considerations in pension schemes - 1.3.1-Pension reform for public sectors; 1.3.2-Social pooling of the basic pension component (Combination of basic pension and individual accounts); 1.3.3-Universal social pension models;1.3.4-Multi-tiered design of pension systems (public pension, enterprise annuity and individual pension); 1.3.5-Occupational pension plans for public sectors and private pension plans; 1.3.6-Vesting, indexation and adjustment mechanisms of pension benefit; 1.3.7-Ageing population and possible strategy of dealing with this situation; 1.3.8-Issue related to the informal sector integration in social security schemes; 1.3.9-NDC (notional defined contribution) pension reform; 1.4.1-Improvement of the individual account component in public pension system for urban workers; 1.4.2-Relationship between social-economic development and the redistribution function of social security; 1.4.3-Strategy of integrating social security system in urban and rural context also through the portability of social insurances.
Topic introduced in 2018
Previous years'topics